## Phase 1 - Quick wins
ID | Feature / Area | Test case | Steps | Expected result | Test as role | Pass / Fail | Notes
1.1 | See passwords | Reveal staff login credentials | User Management → toggle 'Show logins' | Email, password and POS PIN become visible for each staff with a login | Store Admin | PASS | Show-logins toggle reveals email/password/PIN.
1.2 | Staff end date | Record a leaving date | Staff Directory → open profile → Edit → set End date → Save | End date saved and shown on profile; status can be set to Left | Manager | PASS | End date saved on add + edit, shown on profile.
1.3 | Same-name staff | Add two people with identical names | Staff Directory → add 'Chirag Agarwal' twice | Second one auto-named 'Chirag Agarwal 2' | Store Admin | PASS | uniqueDisplayName auto-suffixes ' 2'.
1.4 | POS PIN | Auto-generate a 4-digit PIN | Add staff → click Auto next to PIN | Unique 4-digit PIN generated; duplicates rejected on save | Store Admin | PASS | genPin excludes used PINs; duplicate rejected on save.
1.5 | Optional admin login | Create staff without a website login | Add staff, leave 'Admin website access' unchecked | Staff saved with no email/password; PIN still works | Store Admin | PASS | No login path works; PIN still generated.
1.6 | Daily checklist reset | Checklist resets next day + history | Checklists → tick items → use Reset / next day | Ticks clear for the new day; prior day archived in History modal | Manager | PASS | checkedDate rollover + pushHist archive + History modal.
1.7 | Training redirect link | Open external training | Training → module with link → open assignment → Open external training | Opens the external URL in a new tab | Staff | PASS | assignment.link opens new tab from AssignmentDetail.
1.8 | Shift click shows note | View a shift's note | Shift Planner → click a shift cell | Detail modal opens with day/time/role/venue/notes (not instant delete) | Manager | PASS | Cell click opens detail modal; delete only inside modal.

## Phase 2 - Stations
ID | Feature / Area | Test case | Steps | Expected result | Test as role | Pass / Fail | Notes
2.1 | Settings page access | Only admins see Settings | Sign in as manager vs store admin | Manager: no Settings nav; Store Admin/Owner: Settings visible | Both | PASS | FIXED during audit: page had no route guard (nav was hidden but URL rendered read-only). Added can('settings','view') guard.
2.2 | Create station | Add a station to a venue | Settings → Stations → pick venue → + Add station (e.g. Grill / BOH) | Station appears in that venue's list with FOH/BOH pill | Store Admin | PASS | saveStation writes {name,area,venueId,order}.
2.3 | Quick-add stations | Use suggested stations | Settings → Stations → Quick add buttons | Clicking adds the station; button disables once added | Store Admin | PASS | Quick-add disables once station exists.
2.4 | Per-venue stations | Stations are venue-specific | Add 'Grill' to Mad Benji only, switch venue tab | Grill shows only under Mad Benji | Store Admin | PASS | Stations stored under venues/{id}/stations; all consumers filter by venueId.
2.5 | Roles CRUD | Add/remove a role | Settings → Roles → add 'Waitress' / remove one | Role list updates; new role appears in staff & shift role pickers | Store Admin | PASS | Roles persisted on group doc; used in staff + shift pickers.
2.6 | Assign stations to staff | Pick stations on a profile | Staff → add/edit → Stations picker (filtered by chosen venues) | Only stations of the staff's venues show; saved on profile | Store Admin | PASS | StationPicker filtered by venueIds; saves stationIds+stationNames.
2.7 | Station on shift | Set a station for a shift | Shift Planner → Add shift → choose Station | Station saved; shows in shift cell & detail | Manager | PASS | Shift station select; saved + shown in cell & detail.
2.8 | Station on checklist | Tag a checklist with a station | Checklists → edit → Station (optional) | Station pill shows on the checklist card | Manager | PASS | Checklist station select + card pill.
2.9 | Station on training | Tag a module with a station | Training → edit module → Station (optional) | Station pill shows on the module card | Manager | PASS | Training station select + card pill.

## Phase 3 - Records & audit
ID | Feature / Area | Test case | Steps | Expected result | Test as role | Pass / Fail | Notes
3.1 | Role/venue history | Changes are logged on the profile | Staff → edit role/venue/station/status → Confirm & save | 'Role & venue history' lists each change with date + who | Store Admin | PASS | diffStaff() appends history via arrayUnion (ISO date, no serverTimestamp).
3.2 | Change double-confirm | Confirmation before saving | Staff → edit → Save changes | A confirm banner appears; must click 'Confirm & save' | Store Admin | PASS | Two-step Confirm & save + audit write.
3.3 | Coaching record | Log a coaching note | Staff profile → Coaching & mistake records → add (Coaching/Mistake/…) | Entry added with type pill, note, date and author; removable | Manager | PASS | records[] add/remove with unique id; newest-first.
3.4 | Super-admin activity feed | Sensitive changes notify super admin | Super Admin → Restaurant Groups → Activity button | Edits/permission changes/new staff appear; NEW badge + count | Super Admin | PASS | Activity modal lists auditLog live; NEW badge + row count. Note: row count is one-time fetch, refreshes on reload.
3.5 | Mark activity read | Clear the NEW badge | Activity modal → Mark all read | Items lose NEW highlight; row badge count resets | Super Admin | PASS | Mark all read batch-sets seenBySuper + clears count.
3.6 | Permission change logged | Permission edits are audited | User Management → edit permissions → save | Audit entry 'Permissions changed for …' appears in Activity | Store Admin | PASS | Permission save writes perms.update audit entry.

## Phase 4 - Messaging
ID | Feature / Area | Test case | Steps | Expected result | Test as role | Pass / Fail | Notes
4.1 | Post announcement | Broadcast to all venues | Messages → Announcements → write → All venues → Post | Announcement appears for everyone in scope | Manager | PASS | postAnnouncement scope 'all'; gated by can('messages','edit').
4.2 | Venue-scoped announcement | Target a single venue | Messages → Announcements → choose a venue → Post | Only staff of that venue see it | Manager | PASS | visibleAnns filters by myVenueIds for venue-scoped posts.
4.3 | Acknowledge | Confirm read of an announcement | Open an announcement → Acknowledge | Shows ✓ Acknowledged; acknowledged count increments | Staff | PASS | Acknowledge arrayUnion + count; re-ack guarded.
4.4 | Direct message | Two-way chat | Messages → Direct → + New → pick a person → send | Message appears in thread; recipient sees it in their list | Manager | PASS | sendMessage writes conv=convId(); appears in thread.
4.5 | Unread badge | Sidebar shows unread count | Receive a DM / new announcement | Messages nav shows a badge; clears when read | Staff | PASS | unreadMessages badge = DMs + un-acked; own items pre-seeded read.
4.6 | Read receipts | Opening a thread marks read | Open a conversation with unread messages | Unread count for that thread clears | Manager | PASS | Opening thread marks incoming read; count clears.
4.7 | Permission gating | Staff can read but not post announcements | Sign in as staff | Staff can view & acknowledge; compose box hidden | Staff | PASS | Staff = view; compose hidden, acknowledge still shown. Identity match verified consistent.

## Phase 5 - Shifts & prep
ID | Feature / Area | Test case | Steps | Expected result | Test as role | Pass / Fail | Notes
5.1 | Trainer verifies training | Trainer confirms competency | Training/Staff → open assignment → Trainer verification → Verify | Shows ✓ Verified by <name> + note; ✓ Verified pill on profile | Manager (trainer) | PASS | Verify writes to correct trainingAssignments path; ✓ pill on profile.
5.2 | Remove verification | Undo a verification | Open verified assignment → Remove verification | Reverts to not verified | Manager | PASS | Remove verification works (verifiedAt left stale — cosmetic).
5.3 | Time-based checklist | Set a scheduled time | Checklists → edit → Scheduled time (e.g. 07:15) | ⏰ time pill shows; list sorted by time | Manager | PASS | time field saved; list time-sorted.
5.4 | Due-now highlight | Overdue checklist flagged | Set a checklist time earlier than now, leave items unticked | Card highlighted with 'Due now' pill | Manager | PASS | Due-now: zero-padded HH:MM string compare correct.
5.5 | Prep list carryover | Items persist across days | Checklists → Prep list → add item → next day | Item still present (does NOT reset like checklists) | Manager | PASS | Prep list has no daily-reset logic — carries over.
5.6 | Prep item note + qty | Add detail to a prep item | Prep list → add with Qty + Note / edit Note | Qty (× n) and 📝 note shown under the item | Staff | PASS | qty + editable note render with the item.
5.7 | Reset prep ticks | Clear done items for next service | Prep list → tick some → Reset ticks | All ticks clear; items remain | Manager | PASS | Reset ticks clears done, keeps items.
5.8 | Split-screen planner | Compare two venues side by side | Shift Planner → Split view → choose venue A & B | Two rosters render side by side with per-venue hours | Manager | PASS | Split view = two VenueGrids, venue-scoped cells, per-venue hours.
5.9 | Shift station in cell | Station visible on roster | Split/normal view → shift with a station | Station shown under the time in the cell | Manager | PASS | FIXED during audit: main roster cell now shows station (was venue initials only).

## Regression
ID | Feature / Area | Test case | Steps | Expected result | Test as role | Pass / Fail | Notes
R.1 | Named database | Data reads/writes hit mymor-australia | Any create/edit; check Firebase console (mymor-australia) | Docs land in the named DB, not (default) | Store Admin | PASS | initializeFirestore named DB, not (default).
R.2 | All-venues merge | Selecting 'All venues' merges data | Top venue filter → All venues | Staff/checklists/training/shifts from every venue shown | Owner | PASS | flat() merges per-venue collections for 'All venues'.
R.3 | FOH/BOH filter | Area filter incl. universal | Checklists/Training → FOH / BOH tabs | FOH shows FOH+All; BOH shows BOH+All | Manager | PASS | FOH=FOH+All, BOH=BOH+All in checklists & training.
R.4 | Permission gating | Nav hidden by permission | Set a module to None for a role | That nav item disappears for the role | Store Admin | PASS | Nav filtered by can(key,'view'); 'none' hides it.
R.5 | Rich text items | Bold/colour/highlight persist | Checklist/Training item → format with toolbar → save | Formatting renders back correctly | Manager | PASS | Rich text persisted as HTML and re-rendered.